## Sheet1
Category | AO Part # | Description | Manufacturer | Manufacturer PN | Distributor | Distributor SKU | Qty Per | UOM | Qty to Order | PO | Date | ETA | NOTES
1800
Electronic | EL-CA0030 | 6ft 18AWG Power Cord Cable w/ 3 Conductor PC Power Connector Socket (C13/5-15P) – Black |  |  | Linvox |  | 1 | ea | 1800 | PO07494 | 2015-05-22 | 2015-06-01
Electronic | EL-MS0143 | Conn Fast Receptacle14-16 AWG .250 (2200 Unit Reel) |  | 3-350820-2 | Heilind | 3-350820-2 | 9 | ea | 16200 | PO07624 | 2015-05-11 | 2015-05-15
Electronic | PP-MP0028 | AC Power Entry Modules SC MT FUSED .25" TAB |  |  | Heilind | 161-PF0030/63 | 1 | ea | 1800 | PO07495 | 2015-05-01 | 2015-05-15 | Get these from Heilind for
Electronic | EL-MS0096 | Cartridge Fuses 125V 7A 5X20 MA UL LBC |  |  | Mouser / Digi-Key | 576-0233007.MXP | 2 | ea | 3600 | PO07497/PO06535 | 2015-05-01 | See Notes | These have a silly lead time – pulling in as many as I can - Shipping 596 units 6/16/2015 1,000 units 6/30/2015 3,404 Units 7/3/2015 from Digi Key and then I ordered some from Mouser with a 10 week lead time.
Electronic | EL-MS0248 | CONN RING 14-16 AWG #10 PIDG | TE | 2-36160-1 | Digikey / TTI | A1072TR-ND | 7 | ea | 12600 | PO07497 | 2015-05-01 | 2015-05-15
Electronic | EL-PS0031 | Mean Well Switching Power Supplies 504W 24V 21A Power Supply W/PFC | Mean Well | RSP-500-24 | Linvox | 709-RSP500-24 | 1 | ea | 1800 | PO07038 | 2015-04-23 | 2015-05-15 | Also, had to pull in 150 units from Sager to fill in the gap in lead time from Linvox. See PO07808 150 units x 78.80
Electronic | EL-WR0106 | 16AWG Stranded – Red |  | C2065A.21.03 | Allcable | HU15691626RD | 520 | mm | 936000 | PO07498 | 2015-05-01 | 2015-05-15 | 4 Rolls
Electronic | EL-WR0121 | 16AWG Stranded – Black |  | HU15691626BK | Allcable | HU15691626BK | 380 | mm | 684000 | PO07498 | 2015-05-01 | 2015-05-15 | 3 Rolls
Electronic | EL-WR0124 | 16AWG Stranded – Green w/ yellow stripe |  |  | Allcable |  | 140 | mm | 252000 |  | See Notes |  | .098 per foot x 1,000. The 1000ft spool we have should cover this build
Electronic | EL-WR0123 | 16AWG Stranded – White |  | HU15691626WE | Allcable | HU15691626WE | 190 | mm | 342000 | PO07498 | 2015-05-01 | 2015-05-15 | 2 Rolls
Electronic | EL-MS0246 | Conn Ring 16-22 AWG #4 Red PIDG |  |  | Digikey | A27229CT | 2 | ea | 3600 | PO07109 | 2015-04-09 | 2015-04-15
Electronic | EL-CA0073 | Multi-Conductor Cables 14AWG 4C UNSHLD, BLACK | Belden Wire & Cable | 1310A 010U500 | Mouser | 566-1310A-U500-10 | 1000 | mm | 1800000 | PO06535 | 2015-05-11 | 2015-06-01 | 6,000 Feet (1,800,000 / 304.8 = 5,905.52) Mouser is not going to ship until 6/22 so wrote Allcable PO to pull in 1000 feet for fill in.....
Electronic | TL-CS0136 | Flame-Retardant Heat-Shrink Tubing, 0.21" ID Before Shrinking, 25' Long |  |  | Mcmaster | 7864K32 | 80 | mm | 144000 | PO07499 | 2015-05-01 | 2015-05-04 | 500 Feet
Electronic | EL-MS0249 | Front Mount Male, 4 pin, solder |  |  | WEIPU | SP2112/P41N | 1 | ea | 1800 | PO07280 | 2015-04-15 | 2015-05-15
Electronic | EL-MS0250 | Cable connector female, 4 pin, solder |  |  | WEIPU | SP2110/S4II1N | 1 | ea | 1800 | PO07280 | 2015-04-15 | 2015-05-15
Electronic | EL-SW0023 | SWITCH ROCKER DPST 20A 250V, illuminated red |  |  | Digikey/Heilind | EG1535-ND | 1 | ea | 1800 | PO07497 | 2015-05-01 | See Notes | 1,575 Units 6/4/2015 366 units 7/10/2015
Hardware | HD-MS0290 | Mil. Spec. Grommet, Fits 9/16" Diameter Hole & 1/16" Thick Panel, MS-35489-9 |  |  | Mcmaster | 9307K16 | 1 | ea | 1800 | PO07999 | 2015-06-15 | 2015-06-16
Hardware | HD-BT0155 | Black Alloy Steel Flat-Head Socket Cap Screw, Class 10.9, M4 Size, 6mm Length, .70mm Pitch |  |  | Mcmaster | 91294A186 | 4 | ea | 7200 | PO07499 | 2015-05-01 | 2015-05-04
Hardware | HD-MS0289 | Nylon Loop Clamp, 5/16" ID, Black |  |  | Mcmaster | 8876T37 | 1 | ea | 1800 | PO07999 | 2015-06-15 | 2015-06-16
Hardware | HD-WA0035 | Metric 18-8 Stainless Steel External Serrated Lock Washer, M3 Screw Size, 6mm OD, 0.4mm min Thick |  |  | Mcmaster | 91120A120 | 1 | ea | 1800 | PO07499 | 2015-05-01 | 2015-05-04
Hardware | HD-MS0288 | Adhesive-Back Bumper, Tapered, Polyurethane, 1/2" Wide, 15/64" High, Black |  |  | Mcmaster | 95495K24 | 4 | ea | 7200 | PO07499 | 2015-05-01 | 2015-05-04 | Partial until I can source from EDC.
Hardware | HD-BT0128 | M3 x 6 Bolt, FHCS Black-Oxide |  |  | Fastenal |  | 10 | ea | 18000 | PO07499 | 2015-05-01 | 2015-05-04
Hardware | HD-NT0001 | M3 Nyloc Nut, Zinc Plated |  |  | Fastenal |  | 2 | ea | 3600 | PO07499 | 2015-05-01 | 2015-05-04
Hardware | HD-WA0001 | M3 Washer, Steel, Zinc Plated |  | MTR-M3100321 | Fastenal | MTR-M3100321 | 2 | ea | 3600 | PO07499 | 2015-05-01 | 2015-05-04
Mechanical | PP-MP0096 | Upper PS case, RSP |  |  | Star/Epocs |  | 1 | ea | 1800 | PO07862 | 2015-06-01 | 2015-06-29 | Order with proofs
Mechanical | PP-MP0097 | Lower PS case, RSP |  |  | Star/Epocs |  | 1 | ea | 1800 | PO07862 | 2015-06-01 | 2015-06-29 | Order with proofs
Electronic | EL-MS0254 | FERRITE BRDBAND CYLINDER 17.07MM – 28B0672-000 |  |  | Digikey | 28B0672-000 | 1 | ea | 1800 | PO07872 | 2015-06-01 | 2015-06-05
Electronic | EL-MS0259 | HEATSHRNK DL WL Q53X 3/4"X4'BLK |  |  | Digikey | Q53X034B-ND | 0.066667 | ea | 125 | PO07872 | 2015-06-01 | 2015-06-05
Solder
Laser etching
|  | Allcable – Cable Assembly delivery dates Please see following schedule: June 12th - 100 of each June 19th- 350 per week - Our goal would be to be done with the next 1700 within 5 weeks. |  |  |  | Don't order yet
Items that can be ordered
We have enough/on order
|  | Description | End | Wire | Color | Length | End
|  | Ground wire from Inlet to Stud | EL-MS0143 | EL-WR0124 | Green w/ Yellow | 60mm | EL-MS0246
|  | Ground wire from Stud to PS | EL-MS0246 | EL-WR0124 | Green w/ Yellow | 60mm | EL-MS0248
|  | Neutral line from Inlet to Switch | EL-MS0143 | EL-WR0121 | Black | 70mm | EL-MS0143
|  | Neutral line from Switch to PS | EL-MS0143 | EL-WR0121 | Black | 100mm | EL-MS0248
|  | Live line from Inlet to Switch | EL-MS0143 | EL-WR0123 | White | 70mm | EL-MS0143
|  | Live line from Switch to PS | EL-MS0143 | EL-WR0123 | White | 110mm | EL-MS0248