## Log
Serial Number where implemented is required only during significant changes

Project:			TAZ 6.0 -Olive		Project release date:		April 1, 2016
ECO #	Change Type	ECO Date	Description of Change	Item impacted / (Pn, file, etc.)	New Item / (Pn, file, etc.)	Serial Number or Date implemented	LulzBot Material Disposition
1	Part Design	04/15/2016	Bed plate material change from 5052 to 6061 aluminium to address supplier processing warping	PP-FP0108	PP-MP0145	N/A	Use up inventory
2	Part Design	04/28/16	Change case masking area from 8.00mm to 7.50mm to improve masking exposure possibility due to tolerance stack	PP-FP0075	N/A	N/A	Rework inventory
3	Part Design	05/02/16	Correct through hole size in FreeCAD file to 2.5mm, add through hole dimension to part print; add masking requirement to 5 locations on painted bed plate to improve grounding	PP-FP0108	N/A	N/A	Scrap inventory
4	Part Design	05/05/16	Resize M5 insert through hole size to improve insert retention strength of Bed Mount Chassis	PP-GP0223 v3.3	PP-GP0223 v3.4	KT-PR0041NA-15230	Scrap inventory
5	Processing Change	05/13/16	Addition of TL-CS0114 White Lithium grease to Z drive rods left and right to process instructions and to BOM	N/A	N/A	05/13/16	N/A
7	Processing Change	05/16/16	Update work instruction- changed corner M4 BHCS torque specification to 40 in-lbs from 48 in-lbs; electronic torque drivers released to production to allow torque setting verification; 40 in-lbs backed off of screw break rate	N/A	N/A	05/11/16	N/A

## Change Notifications
Action from Change	Purchased off the shelf item	Purchased make to AO print item	Printed/ Made in house item
New Part Number	Create PN in ERP	Create PN in ERP	Create PN in ERP
	Update BOM	Update BOM	Update BOM
	Create new retail part?	Create new retail part?	Create new retail part?
	Purchase new item	Purchase new item
	Pull MSDS, provide to Facilities
		Create new part model & drawing	Create new part model & drawing
			Create Slice and gcode
	Update Downloads	Update Downloads	Update Downloads
	Apply material disposition (scrap, rework, UAI) to stock items	Apply material disposition (scrap, rework, UAI) to stock items	Apply material disposition (scrap, rework, UAI) to stock items
	Create new Inspection plan	Create new Inspection plan
	review OHAI (update PN references if any, check form factors)	review OHAI (update PN references if any, check form factors)	review OHAI (update PN references if any, check form factors)

	Purchased off the shelf item	Purchased make to AO print item	Printed/ Made in house item
Existing part modification	Update PN in ERP	Update PN in ERP	Update PN in ERP
	Update BOM	Update BOM	Update BOM
	Revised retail part?	Revised retail part?	Revised retail part?
	Purchase new item	Purchase new item
	Pull MSDS, provide to Facilities
		Revise part model & drawing	Revise part model & drawing
			Create Slice and gcode
	Update Downloads	Update Downloads	Update Downloads
	Apply material disposition (scrap, rework, UAI) to stock items	Apply material disposition (scrap, rework, UAI) to stock items	Apply material disposition (scrap, rework, UAI) to stock items
	Revise Inspection plan	Revise Inspection plan
	review OHAI (update PN references if any, check form factors)	review OHAI (update PN references if any, check form factors)	review OHAI (update PN references if any, check form factors)