## Log
Serial Number where implemented is required only during significant changes

Project:			TAZ 6.0 -Olive		Project release date:		April 1, 2016
ECO #	Change Type	ECO Date	Description of Change	Item impacted / (Pn, file, etc.)	New Item / (Pn, file, etc.)	Serial Number or Date implemented	LulzBot Material Disposition
1	Part Design	04/15/2016	Bed plate material change from 5052 to 6061 aluminium to address supplier processing warping	PP-FP0108	PP-MP0145	N/A	Use up inventory
2	Part Design	04/28/16	Change case masking area from 8.00mm to 7.50mm to improve masking exposure possibility due to tolerance stack	PP-FP0075	N/A	N/A	Rework inventory
3	Part Design	05/02/16	Correct through hole size in FreeCAD file to 2.5mm, add through hole dimension to part print; add masking requirement to 5 locations on painted bed plate to improve grounding	PP-FP0108	N/A	N/A	Scrap inventory
4	Part Design	05/05/16	Resize M5 insert through hole size to improve insert retention strength of Bed Mount Chassis	PP-GP0223 v3.3	PP-GP0223 v3.4	KT-PR0041NA-15230	Scrap inventory
5	Processing Change	05/13/16	Addition of TL-CS0114 White Lithium grease to Z drive rods left and right to process instructions and to BOM	N/A	N/A	05/13/2016 / KT-PR0041NA-15376	N/A
6	Hardware Change	Pending	Replace HD-BT004 (Class 12.9 SHCS, Alloy Steel, M5-.8 x 10mm) (X4) to Thread locking M5-.8 x 10 SHCS Black Oxide (x4); TEMPORARY DEVIATION to use M5-.8 x14 mm SHCS (HD-BT0049) until HD-BT0174 is available	HD-BT0048	HD-BT0174	KT-PR0041NA-15635	N/A
7	Processing Change	05/16/16	Update work instruction- changed corner M4 BHCS torque specification to 40 in-lbs from 48 in-lbs; electronic torque drivers released to production to allow torque setting verification; 40 in-lbs backed off of screw break rate	N/A	N/A	05/11/16	N/A
8	Processing Change	05/20/16	Removal of TL-CS0114 White Lithium grease from Z drive rods left and right, removed from process instructions and to BOM	TL-CS0114	N/A	05/20/2016 / KT-PR0041NA-15519	N/A
9	Part Design	05/23/16	Resize M5 & M3 insert through hole size to improve insert retention strength: change M5-.8 x 6.7mm insert length (HD-MS0158) to M5-.8 x 11.1mm insert length (HD-MS0060)	PP-GP0214 v2.7 / (X4) HD-MS0158	PP-GP0214 v2.9 / (x4) HD-MS0060	05/27/2016 printing / KT-PR0041NA-15411	Scrap inventory
10	Part Design	05/23/16	Resize M5 & M3 insert through hole size to improve insert retention strength, lower motor mount 5mm to align pulley with midpoint of idler, resized 12.4mm OD through holes to 12.2mm to address rigidity of Z axis;, change M5-.8 x 6.7mm insert length (HD-MS0158) to M5-.8 x 11.1mm insert length (HD-MS0060)	PP-GP0213 v2.9 / (X4) HD-MS0158	PP-GP0213 v2.10 / (x4) HD-MS0060	05/27/2016 printing / KT-PR0041NA-15670	Scrap inventory
11	Part Design	05/23/16	Move lower 1.65mm x 37.7mm slot in case to a higher location to improve weldability and metal erosion of the slot	PP-MP0110 Rev A	PP-MP0110 Rev B	released to supplier 5/26	Use up inventory
12	Part Design	05/23/16	Add callout of surface finish requirement in areas of laser etching	PP-MP0145 Rev A	PP-MP0145 Rev B	released to supplier 5/26
13	Part Design	05/23/16	Palm project change- Rotate front nut recess 12 degrees to align a flat of the nut to a parallel orientation of the front edge of the printed part, increase part density to 60%, slightly increased size of nut recess to improve nut fit	PP-GP0186 V1.3.2	PP-GP0186 V1.4.1-15C	05/30/2016 Printing / KT-PR0041NA-16243	Scrap inventory
14	INI- Temperature	05/26/16	bearing_holder ini changed to implement fan cooling to address part warping that resulted in bearing bind in ~30% of parts.	bearing_holder_v1.0-16c-m50.250.110-x2	bearing_holder_v1.0-17c-m50.250.110-x2	05/26/2016 printing / KT-PR0041NA-15564	Use up inventory
15	Part Design	05/26/16	Z_Lower_left, M4 mount to frame walls have 2x recesses each that are 2.5mm thick which can cause hardware stack interference allowing Z lower to slip- change is to thicken recess to 3.5mm each; resize 10mm rod holes to 10.2 (set screw hole) and 10.4 (lower hole) to address excess play; until change can be implemented a TEMPORARY DEVIATION to permit use of double washers in each of the mount holes is required.	PP-GP0215 v2.3	PP-GP0215 v2.5	05/26/2016- TDA / 6/6/2016 printing of 2.5 / KT-PR0041NA-15981	Use up inventory
16	Part Design	05/26/16	Z_Lower_Right, M4 mount to frame walls have 2x recesses each that are 2.5mm thick which can cause hardware stack interference allowing Z lower to slip- change is to thicken recess to 3.5mm each; resize 10mm rod holes to 10.2 (set screw hole) and 10.4 (lower hole) to address excess play; until change can be implemented a TEMPORARY DEVIATION to permit use of double washers in each of the mount holes is required.	PP-GP0227 c2.3	PP-GP0227 v2.5	05/26/2016- TDA / 6/6/2016 printing of 2.5 / KT-PR0041NA-15981	Use up inventory
17	Component Change	06/01/16	BOM and Drawing Change for EL-HR0087; / Remove 1x: PC-CN0003 (3 pos conn) / Add 1x: EL-MS0075 (8 pos conn), 6x EL-MS0059 (Female Socket 22-24awg)	PC-CN0003	EL-MS0059 / EL-MS0075	KT-PR0041NA-15730	Rework inventory
18	Component Change	05/23/16	replace SD card with Verbatim model SD card	EL-MS0119	EL-MS0385	KT-PR0041NA-16105	Scrap inventory
19	Component Change	07/18/16	Replace M3x8 BHCS (qty 8 of HD-BT0137) ) used to mount Moon's motor to the Z axis with M3x10 BHCS (qty 8 of HD-BT0148), decreases HD-BT0137 to BOM Qty to 33 and increases HD-BT0148 BOM qty to 24	HD-BT0137	HD-BT0148		Use up inventory
20	Part Design	07/25/16	Z Upper removal of un-necessary radius that hampers assembly and increases size of top side mount holes to				Use up inventory
21	Part Design	07/25/16	PP-MP0145 Rev B to Rev C- Additional masked area notes added, tolerance limits for parts reset at dimension lines	PP-MP0145 Rev B	PP-MP0145 Rev C		Use up inventory
22	Part Design	07/25/16	PP-MP0109 rev C to D- Outer holes (3.4mm) increased to 4.0mm to ease fit of the cover to the case	PP-MP0109 rev C	PP-MP0109 rev D		Use up inventory
23	Part Design	07/25/16	PP-MP0110 rev C to E, Skipped rev D due to an early release of a print before review- Rev D and E changes Updated freeCAD file to correct dimensional error with power entry module (change is noted in RevD), Corrected dimensional allowance for the power entry module, corrected Rev D note (Rev E)	PP-MP0110 Rev C	PP-MP0110 Rev E		Use up inventory

## Change Notifications
Action from Change	Purchased off the shelf item	Purchased make to AO print item	Printed/ Made in house item	Task Owner
New Part Number	Create PN in ERP	Create PN in ERP	Create PN in ERP	Purchasing
	Update BOM	Update BOM	Update BOM	??? (Mfg Eng. Am I taking over BOM control?)
	Create new retail part?	Create new retail part?	Create new retail part?	Purchasing
	Purchase new item	Purchase new item		Purchasing
	Pull MSDS, provide to Facilities			Purchasing
		Create new part model & drawing	Create new part model & drawing	R&D
			Create Slice and gcode	R&D???
	Update Downloads	Update Downloads	Update Downloads	???
	Apply material disposition (scrap, rework, UAI) to stock items	Apply material disposition (scrap, rework, UAI) to stock items	Apply material disposition (scrap, rework, UAI) to stock items	Warehouse
	Create new Inspection plan	Create new Inspection plan		Quality Manager
	review OHAI (update PN references if any, check form factors)	review OHAI (update PN references if any, check form factors)	review OHAI (update PN references if any, check form factors)	Mfg Eng

	Purchased off the shelf item	Purchased make to AO print item	Printed/ Made in house item	Task Owner
Existing part modification	Update PN in ERP	Update PN in ERP	Update PN in ERP	Purchasing
	Update BOM	Update BOM	Update BOM	??? (Mfg Eng. Am I taking over BOM control?)
	Revised retail part?	Revised retail part?	Revised retail part?	Purchasing
	Purchase new item	Purchase new item		Purchasing
	Pull MSDS, provide to Facilities			Purchasing
		Revise part model & drawing	Revise part model & drawing	R&D
			Create Slice and gcode	R&D ???
	Update Downloads	Update Downloads	Update Downloads	???
	Apply material disposition (scrap, rework, UAI) to stock items	Apply material disposition (scrap, rework, UAI) to stock items	Apply material disposition (scrap, rework, UAI) to stock items	Warehouse
	Revise Inspection plan	Revise Inspection plan		Quality Manager
	review OHAI (update PN references if any, check form factors)	review OHAI (update PN references if any, check form factors)	review OHAI (update PN references if any, check form factors)	Mfg Eng

BOM item change				Task Owner
	Temporary Deviation of PN or Quantity of part	Update purchasing plan for both parts, single part increase

	Change from one existing part to another	Update purchasing plan for both parts

	ECO #	Change Type	ECO Date	Description of Change	Item impacted / (Pn, file, etc.)	New Item / (Pn, file, etc.)	Serial Number or Date implemented	LulzBot Material Disposition

	TAZ 6.0 -Olive

## Action Template
Project:	TAZ 6- Olive
ECO#	19
Change:	Replace M3x8 BHCS (qty 8 of HD-BT0137) ) used to mount Moon's motor to the Z axis with M3x10 BHCS (qty 8 of HD-BT0148), decreases HD-BT0137 to BOM Qty to 33 and increases HD-BT0148 BOM qty to 32
Old item	Old Qty	New Item	New Qty	Old Item Disposition
HD-BT0137 / HD-BT0148	49 / 16	HD-BT0137 / HD-BT0148	33 / 32	USE AS IS

Task				Action Owner
Create PN in ERP				N/A
Update BOM				Mfg Eng
Create new retail part?				N/A
Purchase new item				Purchasing
Pull MSDS, provide to Facilities				N/A
Create new part model & drawing				N/A
Create Slice and gcode				N/A
Update Downloads				Steven
Apply material disposition (scrap, rework, UAI) to stock items				N/A
Create new Inspection plan				N/A
review OHAI (update PN references if any, check form factors)				Mfg Eng
Update materials at work stations