## Costed_BOM
PRELIMINARY		TAZ BOM

Category	Status	Description	Manufacturer	Manufacturer PN	Distributor	Distributor SKU	Qty Per	UOM	Comment	Lead Time (wks)	Notes
Accessories	needs to be created	Label, Taz 3D printer barcode					1	ea		1	http://www.uline.com/Product/Detail/S-13010/Anti-static-Poly-Sheeting/48-x-500-4-Mil-Anti-Static-Poly-Sheeting-Roll
Accessories	on order	Box, Shipping, 31ish x 24ish x 13ish	Open				1	ea		2	See MM Quote
Accessories	on order	Foam Kit	Open				1	ea		2	http://www.uline.com/Product/Detail/S-12356FO/Cable-Ties-Tools/18-Fluorescent-Orange-Nylon-Cable-Ties
Accessories	In Stock	9 x 12" 4 Mil Reclosable Bags			Uline	S-1304	1	ea		1
Documentation	being printed	Test acceptance record					1	ea
Documentation	being printed	Quality checklist					1	ea
Documentation	needs final review	Packing list					1	ea
Documentation	needs final review	Unpacking Instructions/QuickStart Guide	Aleph Objects		Aleph Objects		1	ea		1
Documentation	on order	User Manual	Aleph Objects		Aleph Objects		1	ea		3	No clear supplier chosen yet
Electronic	In Stock	Power Supply 12V, 30A	TBD		TBD		1	ea	12V 30A power supply	12
Electronic	In Stock	6ft 18AWG Power Cord Cable w/ 3 Conductor PC Power Connector Socket (C13/5-15P) – Black			Monoprice	5279	1	ea
Electronic	In Stock	Assy, Rambo Controller w/Switches & Connectors	UltiMachine	UMRAMBOPAC	UltiMachine	UMRAMBOPAC	1	ea	Controller	10	Samtec, 1 day standard delivery
Electronic	In Stock	Conn, 2 pin,2.54mm,Black,Gold,thru hole,header,straight	Samtec, Inc.	TSW-102-07-L-S	Digikey	SAM1031-02-ND	1	ea	Fan header for Rambo mod	1	Digikey, 74168 in stock
Electronic	In Stock	Conn, Crimp, .250, 14-16AWG	TE Connectivity	3-350820-2	Digikey	A27824-ND	9	ea	Power switch crimps	1	Digikey for 1000 pc qty, 81825 in stock
Electronic	In Stock	Connector Crimp, Female	Molex Inc.	16-02-0102	Digikey	WM2510-ND	40	ea	Extruder motor extension, buda extension, Y-motor extension, Y-switch extension	1	Digikey, 13664 in stock
Electronic	In Stock	Connector Pins, Male	Molex	16-02-0108	Digikey	WM2565-ND	12	ea	Extruder motor, Y-motor, Y-switch	1
Electronic	In Stock	Heavy Duty Power Connectors HOUSING ONLY, BLACK POWERPOLE 15/45			Mouser	879-1327G6-BK	4	ea	Heat Bed Connector
Electronic	In Stock	Heavy Duty Power Connectors POWERPOLE 15A CONT			Mouser	879-1332-BK	4	ea	Heat Bed Connector		No clear supplier chosen yet
Electronic	In Stock	CONN RECEPT CPC 4POS STD SER 1			Digikey	A1301-ND	1	ea	Main power connector	6-8
Electronic	In Stock	CONN PLUG CPC 4POS STD SER 1			Digikey	A1300-ND	1	ea	Cord Plug
Electronic	In Stock	CONN CABLE CLAMP CPC SIZE 11 BLK			Digikey	A32515-ND	1	ea	Strain Relief
Electronic	In Stock	CONTACT SKT 14-18AWG CRIMP TIN			Digikey	1-66360-6-ND	4	ea	pins
Electronic	In Stock	CONTACT PIN 14-18AWG CRIMP TIN			Digikey	1-66361-6-ND	4	ea	sockets		Digikey, 24663 in stock
Electronic	In Stock	Connector, 4 pin Female housing with latch	Molex	50579404	Digikey	WM2902-ND	8	ea	Motors, extruder extension, y-motor extension	1	Avnet, 1390 in stock
Electronic	In Stock	Connector, 4 pin Male housing with latch	Molex	701070003	Digikey	WM2535-ND	2	ea	Extruder extension, Y motor extension	1
Electronic	In Stock	CONN HOUSING 2POS .100 W/LATCH			Digikey	WM2900-ND	4	ea	Thermistor Extensions, Y switch extension
Electronic	In Stock	CONN HOUSING MALE 2POS .100			Digikey	WM2533-ND	2	ea	Thermistor Extensions, Y switch extension
Electronic	In Stock	FAN,12VDC,Sleeve,5.75CFM,40×40×10 MM,120mA, 6000RPM,1.44W,280MM LEADS,CE/RoHS	Kysan	1531067			1	ea	Electronics enclosure fan	1
Electronic	In Stock	Heater, Silicone 300mmx300mm with Themostor	QU-BD.com				1	ea		4	Digikey, 1473 in stock
Electronic	In Stock	Switch	Arcolectric	C1350ARBB-602AW	Digikey	1091-1019-ND	1	ea	Main power switch	1	See AllCable Quote; 500' min
Electronic	In Stock	Wire, Red, 16AWG Stranded			Mcmaster-Carr Supply Company	7587K962	2840	mm	Internal wiring, DC Power in	1	See AllCable Quote; 500' min
Electronic	In Stock	Wire, Yellow, 16AWG Stranded			McMaster-Carr Supply Company	7587K963	470	mm	Internal wiring	1
Electronic	In Stock	Wire - Single Conductor 16AWG Purple, 100'			Mcmaster-Carr Supply Company	7587K079	3310	mm	Bed Extension, DC Power in
Electronic	In Stock	Stranded Single-Conductor Wire, UL 1007/1569, 24 AWG, 300 VAC, Yellow, 100' Length			Mcmaster-Carr Supply Company	7587K923	1240	mm	Bed Extension
Electronic	In Stock	Stranded Single-Conductor Wire, UL 1007/1569, 24 AWG, 300 VAC, Black, 100' Length			Mcmaster-Carr Supply Company	7587K921	1640	mm
Electronic	In Stock	Stranded Single-Conductor Wire, UL 1007/1569, 24 AWG, 300 VAC, Blue, 100' Length			Mcmaster-Carr Supply Company	7587K28	1640	mm
Electronic	In Stock	Stranded Single-Conductor Wire, UL 1007/1569, 24 AWG, 300 VAC, Green, 100' Length			Mcmaster-Carr Supply Company	7587K19	1640	mm
Electronic	In Stock	Stranded Single-Conductor Wire, UL 1007/1569, 24 AWG, 300 VAC, Orange, 100' Length			Mcmaster-Carr Supply Company	7587K929	2600	mm
Electronic	In Stock	Stranded Single-Conductor Wire, UL 1007/1569, 24 AWG, 300 VAC, Red, 100' Length			Mcmaster-Carr Supply Company	7587K922	4240	mm
Electronic	In Stock	AC Power Entry Modules SC MT FUSED .25" TAB			Mouser	161-PF0030/63	1	ea
Electronic	In Stock	Rocker Switches & Paddle Switches POWER ROCKER			Mouser	506-PRBSA1-16F-BB0HW	1	ea
Electronic	In Stock	Fuses 125V 7A 5X20 MA UL LBC			Mouser	576-0233007.MXP	2	ea
Firmware	Ready	Firmware, Marlin 2013-Q1	Aleph Objects		Aleph Objects		1	ea		0	See Misumi Quote
Hardware	In Stock	T-nut M5 Thread	Open		Misumi	HNKK5-5	80	ea	frame	2
Hardware	In Stock	Steel Compression Spring Zinc-Pltd Music Wire, 1.00" L,.420" OD,.047" Wire (Pack of 12)			McMasterCarr	9657K308	2	ea	Z axes spring	1
Hardware	In Stock	Feed Tube, PTFE			McMaster-Carr Supply Company	5239K12	850	mm	Filament Guide	1
Hardware	In Stock	M3-.5 3.8mm Heatset Insert			McMasterCarr	94180A331	110	ea		1
Hardware	In Stock	M5-.8 11mm Heatset Insert			McMasterCarr	94180A363	4	ea	4 reqd	1	See LSM Quote
Hardware	In Stock	Hobbed, M8 x 60 Hex Head Bolt			Loveland Screw Machine		1	ea	extruder	2
Hardware	In Stock	M3 Nut, Zinc Plated	Open		McMaster-Carr Supply Company	90591A121	2	ea	small herringbone gear, extruder idler	1
Hardware	In Stock	M3 Set Screw (Grub Screw)	Open		McMaster-Carr Supply Company	91390A100	10	ea	extruder, rods and switches	1
Hardware	In Stock	M3 Washer, Steel, Zinc Plated	Open		McMaster-Carr Supply Company	91166A210	88	ea		1
Hardware	In Stock	M3 x 5 Bolt, SHCS Black-Oxide	Open		McMaster-Carr Supply Company	91290A110	26	ea	electronics enclosure	1
Hardware	In Stock	M3 x 12 Bolt, SHCS Black-Oxide	Open		McMaster-Carr Supply Company	91290A117	94	ea		1
Hardware	In Stock	M3 x 25 Bolt, SHCS Black-Oxide	Open		McMaster-Carr Supply Company	91290A125	2	ea	extruder; bed mount, z-hard stop	1
Hardware	In Stock	M4 Nut,Zinc-Plated Steel	Open		McMaster-Carr Supply Company	90591A141	4	ea	extruder/buda	1
Hardware	In Stock	Metric Zinc-Plated Class 5 Steel Wing Nut M4 Screw Size, 0.7mm Pitch	Open		Mcmaster-Carr Supply Company	94300A310	4	ea	shipping clamp
Hardware	In Stock	M4 Washer	Open		McMaster-Carr Supply Company	91166A230	9	ea	Extruder/Buda	1
Hardware	In Stock	Class 10.9 STL Button Head Socket Cap Screw M4 Size, 8 mm Length, .7 mm Pitch	Open		mcMaster-Carr Supply Company	91239A140	3	ea
Hardware	In Stock	M4 x 20 Bolt, SHCS Black-Oxide	Open		McMaster-Carr Supply Company	91290A168	2	ea	Extruder/Buda	1
Hardware	In Stock	Metric 8.8 Zinc-Pltd Steel Hex Head Cap Screw M4 Size, 20mm Length, .7mm Pitch, Fully Threaded	Open		Mcmaster-Carr Supply Company	91280A140	4	ea	shipping clamp
Hardware	In Stock	M4 x 55 Bolt, SHCS Black-Oxide	Open		McMaster-Carr Supply Company	91290A187	2	ea	extruder	1
Hardware	In Stock	M5 Washer, Steel, Zinc Plated	Open		McMaster-Carr Supply Company	91166A240	84	ea	frame	1
Hardware	In Stock	M5 x 10 Bolt, SHCS Black-Oxide	Open		McMaster-Carr Supply Company	91290A224	88	ea	frame	1
Hardware	In Stock	M5 x 14 Bolt, SHCS Black_Oxide	Open		Mcmaster-Carr Supply Company	91290A230	6	ea	If required threading into the end of an extrusion
Hardware	In Stock	M8 Nyloc Nut, Zinc Plated	Open		McMaster-Carr Supply Company	90576A117	3	ea	bearings, extruder	1
Hardware	In Stock	M8 Nut, Zinc Plated	Open		McMaster-Carr Supply Company	90591A161	3	ea	spooler	1
Hardware	In Stock	M8 Washer, Steel, Zinc Plated	Open		McMaster-Carr Supply Company	91166A270	12	ea	extruder, spooler,bearings	1
Hardware	In Stock	M8 Wing Nut, Zinc-Plated Steel	Open		McMaster-Carr Supply Company	94300A340	1	ea	Filament Spooler	1
Hardware	In Stock	M8 x 35 Bolt, BHCS Black-oxide	Open		McMaster-Carr Supply Company	91239A438	2	ea	bearings	1
Hardware	In Stock	Metric Spring Steel Shim - DIN 988 0.5mm Thick, 8mm ID, 14mm OD	Open		McMaster-Carr Supply Company	98055A114	1	ea	extruder - optional hobbed bolt aligner	1
Hardware	In Stock	Metric Spring Steel Shim - DIN 988 1.0mm Thick, 8mm ID, 14mm OD	Open		McMaster-Carr Supply Company	98055A115	1	ea	extruder - optional hobbed bolt aligner	1
Hardware	In Stock	SJ-5023 SERIES BUMPON PROTECTIVE PRODUCTS	Open		JAMECO VALUEPRO	SJ5023BLKC	8	ea	Feet	1
Hardware	In Stock	Spring, Extruder, 6mm OD, 0.8mm WD, 9.7mm FL	Associated Spring	D12110	Associated Spring	C0240-032-0380-M	6	ea	Extruder, Z-endstop	1
Hardware	In Stock	Spring, 4.6mm OD, 0.5mm WD, 19mm	Associated Spring		Associated Spring	C0180-020-0750-M	1	ea	Z stop
Hardware	In Stock	Thumb Screw Knob for M3 SHCS, Red	Open		McMaster-Carr Supply Company	91175A061	1	ea	Z adjuster	1
Hardware	In Stock	Thumb Screw Knob for M4 SHCS, Black	Open		McMaster-Carr Supply Company	91175A062	2	ea	extruder	1
Hardware	In Stock	Thumb Screw Knob for M5 SHCS, Black	Open		McMaster-Carr Supply Company	91175A063	4	ea	Y-axis	1
Hardware	In Stock	Wire Tubing (100' roll)	Panduit	CLT25F-C20	Digikey	298-1141-ND	4420	mm		1
Hardware	In Stock	PVC Tubing 3/16" ID, 5/16" OD, 1/16" Wall Thickness					120	mm	Coupler	1	No clear source
Hardware	In Stock	Standard Nylon Cable Tie 7-1/2" L, 1-7/8" Bundle Dia, 50#Tensile Strg, Black			McMaster-Carr Supply Company	7130K59	4	ea		2
Hardware	In Stock	Wire Tie, 8.5"			McMaster-Carr Supply Company	7130K32	18	ea		1	Used with Silicone rubber heat bed option
Mechanical	In Stock	Loctite RTV Silicone Gasket Maker, Number 59875, 10.15 oz (300 ml) Cartridge, Black			McMaster-Carr Supply Company	6641A42	2	oz		3	See Parker Steel 10mm Quote
Mechanical	In Stock	M8 x 175mm threaded rod					1	ea		1
Mechanical	In Stock	10mm x 500mm smooth rod	Open		Misumi	SSFHR10-500	6	ea		1
Mechanical	In Stock	Metric Brass Hex Nut M6 Size, 1 mm Pitch, 10 mm Width, 5 mm Height	Open		Mcmaster-Carr Supply Company	90690A047	2	ea		3
Mechanical	In Stock	Metric 18-8 Stainless Steel Threaded Rod M6 Size, 410mm			Mcmaster-Carr Supply Company	90024A070	2	ea		4
Mechanical	In Stock	608ZZ bearing	Open		vxb.com	100Skate	7	ea	4 bearings used in robot, 3 in extruder	2	See Datum Quote
Mechanical	In Stock	8mm Smooth Rod x 20mm	Open		Datum Machining, Inc.		1	ea	extruder	2
Mechanical	In Stock	Assy, Budasnozzle 2.0 with 0.35 nozzle	Aleph Objects		Aleph Objects		1	ea		4
Mechanical	In stock	Borosilicate Glass Bed 300mm x 300mm	Allen Scientific				1	ea	Y carriage and Bed Plate	4	See Misumi Quote
Mechanical	In stock	Extrusion 500mm (black)			misumi.com	HFSB5-2020-500	4	ea		4	See Misumi Quote
Mechanical	In stock	Extrusion 500mm (black), tapped on one ends			misumi.com	HFSB5-2020-500-LTP	4	ea		4	See Misumi Quote
Mechanical	In stock	Extrusion 500mm (black), tapped on both ends			misumi.com	HFSV5-2020-500-TPW	2	ea		4	22 available from stock; https://sdp-si.com/eStore/PartDetail.asp?Opener=Group&PartID=49992&GroupID=342
Mechanical	In stock	GT2 1164mm by 6mm belt			B & B Manufacturing, Inc	1164-2P-06 (2MR-1164-06)	2	ea	Y and X drive	7	See B&B Quote
Mechanical	In stock	GT2 Timing Pulley, 5mm Bore Aluminum			B & B Manufacturing, Inc	16-2P06M6CA5 5MM BORE ALUMINUM	2	ea	Y and X drive	1	See Desen Weier Quote; Freight charges amortized
Mechanical	In stock	IGUS drop in for LM10UU			IGUS	RMJ-01-10	11	ea		2
Mechanical	In Stock	NEMA 17 Stepper Motors	Soyo	SY42STH47-1504A	Aleph Objects		5	ea		8
Mechanical	In Stock	Super Lube Oil with PTFE Teflon 51004 4oz Bottle	Super Lube	51004	AAA INDUSTRIAL SUPPLY	305008	0.1	oz
Printed	In process	double_bearing_holder	Aleph Objects		Aleph Objects	Double_Bearing_Holder.stl	3	ea
Printed	In process	bearing_holder	Aleph Objects		Aleph Objects	Bearing_Holder.stl	5	ea
Printed	In process	belt_clamp	Aleph Objects		Aleph Objects	BeltClamp.stl	2	ea
Printed	In process	electronics_enclosure_bottom	Aleph Objects		Aleph Objects	ElectronicsEnclosureBottom.stl	1	ea
Printed	In process	electronics_enclosure_front	Aleph Objects		Aleph Objects	Part of ElectronicsEnclosureSides.stl	1	ea
Printed	In process	electronics_enclosure_strain_relief	Aleph Objects		Aleph Objects	Part of ElectronicsEnclosureSides.stl	1	ea
Printed	In process	electronics_enclosure_strain_side	Aleph Objects		Aleph Objects	Part of ElectronicsEnclosureSides.stl	1	ea
Printed	In process	electronics_enclosure_switch	Aleph Objects		Aleph Objects	Part of ElectronicsEnclosureSides.stl	1	ea
Printed	In process	electronics_enclosure_top	Aleph Objects		Aleph Objects	ElectronicsEnclosureTop.stl	1	ea
Printed	In process	electronics_enclosure_power	Aleph Objects		Aleph Objects	Part of ElectronicsEnclosureSides.stl	1	ea
Printed	In process	feed_tube_holder	Aleph Objects		Aleph Objects	FilamentGuide.stl	1	ea
Printed	In process	feed_tube spinner	Aleph Objects		Aleph Objects		1	ea
Printed	In process	frame_connector	Aleph Objects		Aleph Objects	FrameConnectors.stl	8	ea
Printed	In process	name_plate	Aleph Objects		Aleph Objects	NamePlate.stl	1	ea
Printed	In process	herringbone_large_gear	Aleph Objects		Aleph Objects		1	ea	extruder
Printed	In process	herringbone_small_gear	Aleph Objects		Aleph Objects		1	ea	extruder
Printed	In process	Wade Reloaded Bearing Washer	Aleph Objects		Aleph Objects		1	ea	extruder
Printed	In process	Wade Reloaded Extruder Block	Aleph Objects		Aleph Objects		1	ea	extruder
Printed	In process	Wade Reloaded Idler Block	Aleph Objects		Aleph Objects		1	ea	extruder
Printed	In process	extruder_latch	Aleph Objects		Aleph Objects		1	ea
Printed	In process	x_bearing_mount	Aleph Objects		Aleph Objects	X_BearingForSpring.stl	1	ea
Printed	In process	x_carriage	Aleph Objects		Aleph Objects	X_Carriage.stl	1	ea
Printed	In process	x_carriage_guide	Aleph Objects		Aleph Objects	X_Charriage_QuickGuide.stl	1	ea
Printed	In process	x_motor_mount	Aleph Objects		Aleph Objects	X_MotorForSpring	1	ea
Printed	In process	extruder_mount	Aleph Objects		Aleph Objects	X_SingleExtruderMount.stl	1	ea
Printed	In process	y_bearing_mount	Aleph Objects		Aleph Objects	Y_Bearing.stl	1	ea
Printed	In process	y_belt_mount	Aleph Objects		Aleph Objects	Y_BeltMount.stl	1	ea
Printed	In process	y_mount_chassis	Aleph Objects		Aleph Objects	Part of Y_FrameConnector2.stl	4	ea
Printed	In process	y_mount_table	Aleph Objects		Aleph Objects	Part of Y_FrameConnector2.stl	4	ea
Printed	In process	y_motor_mount	Aleph Objects		Aleph Objects	Y_Motor.stl	1	ea
Printed	In process	z_motor_mount	Aleph Objects		Aleph Objects	Z_MotorMount.stl	2	ea
Printed	In process	z_nut_spring_m6	Aleph Objects		Aleph Objects	X_Nut_Spring.stl	2	ea
Printed	In process	z_top	Aleph Objects		Aleph Objects	Z_Top.stl	2	ea
Printed	In process	Spool Holder - Inner	Aleph Objects		Aleph Objects		1	ea
Printed	In process	Spool Holder - Outer	Aleph Objects		Aleph Objects		1	ea
Printed	In process	bed_finger	Aleph Objects		Aleph Objects		4	ea
Printed	In process	bed_corner	Aleph Objects		Aleph Objects		4	ea
Printed	In process	powerbox	Aleph Objects		Aleph Objects		1	ea
Printed	In process	shipping_clamp_a	Aleph Objects		Aleph Objects		4	ea				Food Machinery of America Inc. Omcan Food Machinery
Printed	In process	shipping_clamp_b	Aleph Objects		Aleph Objects		4	ea
Sheetmetal	In Stock	Bed Mount Plate, Aluminum	EPOCS		Aleph Objects		1	ea	Y carriage and Bed Plate	3
Tools	In Stock	Tool Kit Bag w/ LulzBot logo		TL-MS0001	Specialty incentives Inc.		1	ea
Tools	In Stock	Small Size Hand Brush Acetal Hndl, Flat .003" Bristle, SS, 1/8" X 1/16"		TL-HD0006	Mcmaster-Carr Supply Company	33335k2	1	ea
Tools	In Stock	Pro Dental Pick, 5 3/4 in		TL-HD0007	PRECISION PRODUCTS.US	J1031S	1	ea
Tools	In Stock	Stainless Steel Pocket Rule Semiflexible, Metric Grads, 150 mm Length		TL-HD0008	McMaster-Carr Supply Company	6813a62	1	ea
Tools	In Stock	7 1/2" Nylon Handle Clam Knife		TL-HD0009	WEBstaurant Store	35340592	1	ea
Tools	In Stock	Standard Precision Knife, 4-7/8" Handle Length		TL-HD0010	McMaster-Carr Supply Company	35435a11	1	ea
Tools	In Stock	Stainless Steel General Purpose Tweezers Bent Tip, Serrated Inside, 7" Length		TL-HD0011	Mcmaster-Carr Supply Company	7005A12	1	ea
Tools	In Stock	Stanley 84-031 6" Bi-Material Long Nose Pliers		TL-HD0012	CREATIVE HOME AND GARDENING		1	ea
Tools	In Stock	Ball-Point Hex Set L-Key, 15 PC, 1.27mm-10mm		TL-HD0013	Staples	698318	1	ea
Tools	In Stock	HDPE, 8 oz. Natural Large Round Wide-Mouth Jars		TL-MS0002	Uline	S-18070	1	ea
Tools	In Stock	Standard-Head Open-End Wrench Black Finish, 13mm Sz, 4-7/8" Length, 15 Deg Angle		TL-HD0014	Mcmaster-Carr Supply Company	5488A19	1	ea
Tools	In Stock	2 x 2" D.O.T. Labels - "Right to Know"		TL-MS0003	Uline	S-2845	1	ea