## 08.04.16-BOM-Order
Longfin BOM |  |  |  | QTY TO BUILD |  | 512
Category | AO Part # | Part Name | Manufacturer |  | Distributor | Dis PN | Qty | UOM | Qty to order | PO | Date | ETA | Notes
Printed | PP-GP0197 | dual_extruder_2.0_mount_v1.0 | Aleph Objects |  | Aleph Objects |  | 1 | ea | 512 | N/A | 2016-08-18 |  | added Task: Parts needed for Longfin x 512 units - TAZ Dually Flexy v2 (MO16-0057 & MO16-0062)
Printed | PP-GP0198 | javelin_flex_plate_v1.2 | Aleph Objects |  | Aleph Objects |  | 1 | ea | 512 | N/A | 2016-08-18 |  | added Task: Parts needed for Longfin x 512 units - TAZ Dually Flexy v2 (MO16-0057 & MO16-0062)
Printed | PP-GP0199 | 40mm_fan_duct__for_dual_v0.3 | Aleph Objects |  | Aleph Objects |  | 2 | ea | 1024 | N/A | 2016-08-18 |  | added Task: Parts needed for Longfin x 512 units - TAZ Dually Flexy v2 (MO16-0057 & MO16-0062)
Printed | PP-GP0186 | Wade extruder body for Hex nozzle v1.0 | Aleph Objects |  | Aleph Objects |  | 1 | ea | 512 | N/A | 2016-08-18 |  | added Task: Parts needed for Longfin x 512 units - TAZ Dually Flexy v2 (MO16-0057 & MO16-0062)
Printed | PP-GP0200 | Flexystruder Body V2.0 - for hexagon, Green | Aleph Objects |  | Aleph Objects |  | 1 | ea | 512 | N/A | 2016-08-18 |  | added Task: Parts needed for Longfin x 512 units - TAZ Dually Flexy v2 (MO16-0057 & MO16-0062)
Printed | PP-GP0193 | Wade Reloaded Idler Block v1.4, Taz & Mini | Aleph Objects |  | Aleph Objects |  | 1 | ea | 512 | N/A | 2016-08-18 |  | added Task: Parts needed for Longfin x 512 units - TAZ Dually Flexy v2 (MO16-0057 & MO16-0062)
Printed | PP-GP0191 | Herringbone Large Gear v1.3, Lulzbot green | Aleph Objects |  | Aleph Objects |  | 1 | ea | 512 | N/A | 2016-08-18 |  | added Task: Parts needed for Longfin x 512 units - TAZ Dually Flexy v2 (MO16-0057 & MO16-0062)
Printed | PP-GP0061 | Herringbone Large Gear v1.3, Black | Aleph Objects |  | Aleph Objects |  | 1 | ea | 512 | N/A | 2016-08-18 |  | added Task: Parts needed for Longfin x 512 units - TAZ Dually Flexy v2 (MO16-0057 & MO16-0062)
Printed | PP-GP0091 | extruder_latch_v2.0 | Aleph Objects |  | Aleph Objects |  | 1 | ea | 512 | N/A | 2016-08-18 |  | added Task: Parts needed for Longfin x 512 units - TAZ Dually Flexy v2 (MO16-0057 & MO16-0062)
Printed | PP-GP0192 | Herringbone Small Gear v1.1, Lulzbot green | Aleph Objects |  | Aleph Objects |  | 1 | ea | 512 | N/A | 2016-08-18 |  | added Task: Parts needed for Longfin x 512 units - TAZ Dually Flexy v2 (MO16-0057 & MO16-0062)
Printed | PP-GP0062 | Herringbone Small Gear v1.1, Black | Aleph Objects |  | Aleph Objects |  | 1 | ea | 512 | N/A | 2016-08-18 |  | added Task: Parts needed for Longfin x 512 units - TAZ Dually Flexy v2 (MO16-0057 & MO16-0062)
Printed | PP-GP0060 | Extruder Washer v3.0, Taz | Aleph Objects |  | Aleph Objects |  | 2 | ea | 1024 | N/A | 2016-08-18 |  | added Task: Parts needed for Longfin x 512 units - TAZ Dually Flexy v2 (MO16-0057 & MO16-0062)
Printed | PP-GP0109 | Spool Arm, TAZ | Aleph Objects |  | Aleph Objects |  | 1 | ea | 512 | N/A | 2016-08-18 |  | added Task: Parts needed for Longfin x 512 units - TAZ Dually Flexy v2 (MO16-0057 & MO16-0062)
Printed | PP-GP0074 | feed_tube spinner | Aleph Objects |  | Aleph Objects |  | 1 | ea | 512 | N/A | 2016-08-18 |  | added Task: Parts needed for Longfin x 512 units - TAZ Dually Flexy v2 (MO16-0057 & MO16-0062)
Printed | PP-GP0203 | T-nut holding jig, Dual Extruder 2.0 | Aleph Objects |  | Aleph Objects |  | 1 | ea | 512 | N/A | 2016-08-18 |  | added Task: Parts needed for Longfin x 512 units - TAZ Dually Flexy v2 (MO16-0057 & MO16-0062)
Hardware | HD-MS0031 | Thumb Screw Knob for M4 SHCS, Black | Fastenal | 11102951 | Fastenal | 11102951 | 2 | ea | 1024 | PO15128 | 2016-08-17 | 2016-08-22 | Combining MO16-0056, MO16-0057, MO16-0061, and MO16-0062 ~AS
Hardware | HD-BT0052 | M4 x 55 Bolt, SHCS Black-Oxide | Fastenal | ZT2530055PF000 | Fastenal |  | 2 | ea | 1024 | PO15128 | 2016-08-17 | 2016-08-22 | Combining MO16-0056, MO16-0057, MO16-0061, and MO16-0062 ~AS
Hardware | HD-NT0004 | M3 Nut, Zinc Plated | Fastenal | 40302 | Fastenal |  | 3 | ea | 1536 | PO15128 | 2016-08-17 | 2016-08-22 | Combining MO16-0056, MO16-0057, MO16-0061, and MO16-0062 ~AS
Hardware | HD-BT0012 | M3 Set Screw (Grub Screw) | Fastenal | 40818 | Fastenal |  | 2 | ea | 1024 | PO15128 | 2016-08-17 | 2016-08-22 | Combining MO16-0056, MO16-0057, MO16-0061, and MO16-0062 ~AS
Hardware | HD-BT0039 | M3 x 12 Bolt, SHCS Black-Oxide | Fastenal | 39505 | Fastenal | 39505 | 6 | ea | 3072 | PO15128 | 2016-08-17 | 2016-08-22 | Combining MO16-0056, MO16-0057, MO16-0061, and MO16-0062 ~AS
Hardware | HD-BT0135 | M3 x 25 Bolt, FHCS Black-Oxide | Fastenal | 40929 | fastenal | 40929 | 2 | ea | 1024 | PO15128 | 2016-08-17 | 2016-08-22 | Combining MO16-0056, MO16-0057, MO16-0061, and MO16-0062 ~AS
Hardware | HD-BT0041 | M3 x 25 Bolt, SHCS Black-Oxide | Fastenal | 39508 | Fastenal | 39508 | 3 | ea | 1536 | PO15128 | 2016-08-17 | 2016-08-22 | Combining MO16-0056, MO16-0057, MO16-0061, and MO16-0062 ~AS
Hardware | HD-WA0001 | M3 Washer, Steel, Zinc Plated | Fastenal | 40352 | Fastenal | 40352 | 13 | ea | 6656 | PO15128 | 2016-08-17 | 2016-08-22 | Combining MO16-0056, MO16-0057, MO16-0061, and MO16-0062 ~AS
Hardware | HD-BT0046 | M4 x 16 Bolt, SHCS Black-Oxide | Fastenal | 39526 | Mcmaster | 91290A154 | 4 | ea | 2048 | PO15128 | 2016-08-17 | 2016-08-22 | Combining MO16-0056, MO16-0057, MO16-0061, and MO16-0062 ~AS
Hardware | HD-WA0005 | M4 Washer | Fastenal | 40353 | Fastenal |  | 4 | ea | 2048 | PO15128 | 2016-08-17 | 2016-08-22 | Combining MO16-0056, MO16-0057, MO16-0061, and MO16-0062 ~AS
Hardware | HD-NT0011 | M4 Nut, Steel, Zinc Plated | Fastenal | 40303 | Fastenal |  | 6 | ea | 3072 | PO15128 | 2016-08-17 | 2016-08-22 | Combining MO16-0056, MO16-0057, MO16-0061, and MO16-0062 ~AS
Hardware | HD-NT0002 | M8 Nyloc Nut, Zinc Plated | Fastenal | 40163 | Fastenal |  | 2 | ea | 1024 | PO15128 | 2016-08-17 | 2016-08-22 | Combining MO16-0056, MO16-0057, MO16-0061, and MO16-0062 ~AS
Hardware | HD-WA0008 | M8 shim washer - .5mm | Fastenal | 11511045 | Fastenal |  | 2 | ea | 1024 | PO15128 | 2016-08-17 | 2016-08-22 | Combining MO16-0056, MO16-0057, MO16-0061, and MO16-0062 ~AS
Hardware | HD-WA0009 | M8 shim washer – 1.0mm | Fastenal | 11511046 | Fastenal |  | 2 | ea | 1024 | PO15128 | 2016-08-17 | 2016-08-22 | Combining MO16-0056, MO16-0057, MO16-0061, and MO16-0062 ~AS
Hardware | HD-WA0006 | M8 Washer, Steel, Zinc Plated | Fastenal | 1140357 | Fastenal |  | 6 | ea | 3072 | PO15128 | 2016-08-17 | 2016-08-22 | Combining MO16-0056, MO16-0057, MO16-0061, and MO16-0062 ~AS
Hardware | HD-BT0104 | M3 x 8 BHCS, Stainless | Fastenal | MB2510008A20000 | Fastenal |  | 3 | ea | 1536 | PO15128 | 2016-08-17 | 2016-08-22 | Combining MO16-0056, MO16-0057, MO16-0061, and MO16-0062 ~AS
Hardware | HD-BT0007 | M3 x 20 SCHS, black-oxide | Fastenal | 91290A123 | Fastenal | 91290A123 | 4 | ea | 2048 | PO15128 | 2016-08-17 | 2016-08-22 | Combining MO16-0056, MO16-0057, MO16-0061, and MO16-0062 ~AS
Hardware | HD-MS0230 | M2 x 6mm SCHS, black-oxide | Fastenal | 134596 | Fastenal | 134596 | 2 | ea | 1024 | PO15128 | 2016-08-17 | 2016-08-22 | Combining MO16-0056, MO16-0057, MO16-0061, and MO16-0062 ~AS
Hardware | HD-BT0153 | M5 X 20 SCHS, Stainless | Fastenal | MS2540020A40000 | Mcmaster | 92290A242 | 1 | ea | 512 | PO15128 | 2016-08-17 | 2016-08-22 | Combining MO16-0056, MO16-0057, MO16-0061, and MO16-0062 ~AS
Hardware | HD-BT0073 | M5 x 10mm BHCS, black-oxide | Fastenal | 39905 | Fastenal | 39905 | 1 | ea | 512 | PO15128 | 2016-08-17 | 2016-08-22 | Combining MO16-0056, MO16-0057, MO16-0061, and MO16-0062 ~AS
Hardware | HD-BT0049 | M5 x 14 Bolt, SHCS Black_Oxide | Fastenal | 1139539 | Fastenal | 1139539 | 1 | ea | 512 | PO15128 | 2016-08-17 | 2016-08-22 | Combining MO16-0056, MO16-0057, MO16-0061, and MO16-0062 ~AS
Hardware | HD-MS0062 | Metric Aluminum Unthreaded Spacer, 8MM OD, 8MM Length, M5 Screw Size |  | 11485208 | Fastenal | 11485208 | 1 | ea | 512 | PO15128 | 2016-08-17 | 2016-08-22 | Combining MO16-0056, MO16-0057, MO16-0061, and MO16-0062 ~AS
Hardware | HD-WA0007 | M5 Washer, Steel, Zinc Plated | Fastenal | 1140354 | Fastenal | 1140354 | 2 | ea | 1024 | PO15128 | 2016-08-17 | 2016-08-22 | Combining MO16-0056, MO16-0057, MO16-0061, and MO16-0062 ~AS
Hardware | HD-WA0035 | Metric 18-8 Stainless Steel External Serrated Lock Washer, M3 Screw Size, 6mm OD, 0.4mm min Thick |  | 11511313 | Fastenal | 91120A120 | 1 | ea | 512 | PO15128 | 2016-08-17 | 2016-08-22 | Combining MO16-0056, MO16-0057, MO16-0061, and MO16-0062 ~AS
Mechanical | HD-MS0282 | 608-2RS ABEC3/C3 Rubber Sealed Bearing – BLACK | JSB |  | JSB |  | 5 | ea | 2560 | PO15120 | 2016-08-17 | 2016-09-12 | Combining MO16-0056, MO16-0057, MO16-0061, and MO16-0062 ~AS
Hardware | HD-MS0158 | M5-.8 6.7mm Heatset Insert | C.E.H. | PEM IUBB-M5-1 | C.E.H. | PEM IUBB-M5-1 | 1 | ea | 512 | PO15122 | 2016-08-17 | 2016-09-20 | Combining MO16-0056, MO16-0057, MO16-0061, and MO16-0062 ~AS
Hardware | HD-MS0030 | M3-.5 3.8mm Heatset Insert | C.E.H. | IUBB-M3-1 | C.E.H. | IUBB-M3-1 | 4 | ea | 2048 | PO15122 | 2016-08-17 | 2016-09-20 | Combining MO16-0056, MO16-0057, MO16-0061, and MO16-0062 ~AS
Hardware | HD-BT0108 | Hobbed, M8 x 50 Bolt, 26mm offset |  |  | Quattro |  | 2 | ea | 1024 | PO15123 | 2016-08-17 | 2016-09-07 | Combining MO16-0056, MO16-0057, MO16-0061, and MO16-0062 ~AS
Hardware | HD-MS0027 | Spring, Extruder, 6mm OD, 0.8mm WD, 9.7mm FL |  | C0240-032-0380-M | Associated Spring | C0240-032-0380-M | 2 | ea | 1024 | PO15129 | 2016-08-17 | 2016-09-09 | Combining MO16-0056, MO16-0057, MO16-0061, and MO16-0062 ~AS
Mechanical | HD-RD0004 | 8mm Smooth Rod x 18-19mm |  |  | IGUS |  | 1 | ea | 512 | PO15119 | 2016-08-17 | 2016-09-12 | Combining MO16-0056, MO16-0057, MO16-0061, and MO16-0062 ~AS
Mechanical | PP-MP0085 | Bed finger |  |  | MBK | PP-MP0085 | 4 | ea | 2048 | PO15126 | 2016-08-17 | 2016-09-15 | Combining MO16-0056, MO16-0057, MO16-0061, and MO16-0062 ~AS
Mechanical | PP-MP0087 | Hex dual mount plate |  |  | MBK | PP-MP0087 | 1 | ea | 512 | PO15126 | 2016-08-17 | 2016-09-15 | Combining MO16-0056, MO16-0057, MO16-0061, and MO16-0062 ~AS
Mechanical | PP-MP0086 | Dual lower bracket |  |  | MBK | PP-MP0086 | 1 | ea | 512 | PO15126 | 2016-08-17 | 2016-09-15 | Combining MO16-0056, MO16-0057, MO16-0061, and MO16-0062 ~AS
Mechanical | HE-SH0041 | Reprap Modified Hexagon Hotend, Lulzbot Edition, 3.0mm Filament, .6mm Nozzle | Aleph Objects |  | Reprapdiscount |  | 2 | ea | 1024
| PP-MP0133 | AO-Hex Heatsink for 3mm Filament | RepRapDiscount |  | RepRapDiscount |  | 2 | ea | 1024 | PO15112 | 2016-08-16 | 2016-09-15 | Combining MO16-0056, MO16-0057, MO16-0061, and MO16-0062 ~AS
| PP-MP0134 | AO-Hex Heater Bblock with Holes for Retention Plate and Hexagon Logo Laser Etched on Front | RepRapDiscount |  | RepRapDiscount |  | 2 | ea | 1024 | PO15112 | 2016-08-16 | 2016-09-15 | Combining MO16-0056, MO16-0057, MO16-0061, and MO16-0062 ~AS
| PP-MP0139 | 0.6mm Nozzle for 3mm Filament | RepRapDiscount |  | RepRapDiscount |  | 2 | ea | 1024 | PO15112 | 2016-08-16 | 2016-09-15 | Combining MO16-0056, MO16-0057, MO16-0061, and MO16-0062 ~AS
| EL-TH0011 | Semitec GT2 Thermistor (100kOhm type) Thermistor needs 23cm leads with no connectors on end | RepRapDiscount |  | RepRapDiscount |  | 2 | ea | 1024 | PO15112 | 2016-08-16 | 2016-09-15 | Combining MO16-0056, MO16-0057, MO16-0061, and MO16-0062 ~AS
| EL-MS0377 | Heater cartridge 24V 30W Heater Cartridge needs 23cm leads with no connectors on end | RepRapDiscount |  | RepRapDiscount |  | 2 | ea | 1024 | PO15112 | 2016-08-16 | 2016-09-15 | Combining MO16-0056, MO16-0057, MO16-0061, and MO16-0062 ~AS
| PP-MP0136 | Thermistor Retention Plate | RepRapDiscount |  | RepRapDiscount |  | 2 | ea | 1024 | PO15112 | 2016-08-16 | 2016-09-15 | Combining MO16-0056, MO16-0057, MO16-0061, and MO16-0062 ~AS
| PP-MP0137 | Standard Hexagon Mount Plate | RepRapDiscount |  | RepRapDiscount |  | 2 | ea | 1024 | PO15112 | 2016-08-16 | 2016-09-15 | Combining MO16-0056, MO16-0057, MO16-0061, and MO16-0062 ~AS
| HD-BT0172 | M3 x4 Setscrew (Heater Cartridge Set Screw) | RepRapDiscount |  | RepRapDiscount |  | 2 | ea | 1024 | PO15112 | 2016-08-16 | 2016-09-15 | Combining MO16-0056, MO16-0057, MO16-0061, and MO16-0062 ~AS
| HD-BT0173 | Heat Sink Setscrew (M2x6 SCHS) | RepRapDiscount |  | RepRapDiscount |  | 2 | ea | 1024 | PO15112 | 2016-08-16 | 2016-09-15 | Combining MO16-0056, MO16-0057, MO16-0061, and MO16-0062 ~AS
Hardware | HD-TB0007 | Feed Tube, PTFE |  |  | Professional Plastics | 5239K12 | 850 | mm | 435200 | PO15130 | 2016-08-17 | 2016-09-09 | Combining MO16-0056, MO16-0057, MO16-0061, and MO16-0062 ~AS
Hardware | HD-MS0058 | Wire Tie, 8” Black | Mcmaster | 7130K32 | Mcmaster | 7130K32 | 12 | ea | 6144 | N/A |  |  | huge stock on hand ~AS (Approved to use current inventory.TS)
Electronic | EL-MS0014 | Wire ferrules – 1.5mm^2 – 7mm |  |  | Mcmaster | 9681K21 | 4 | ea | 2048 | PO15131 | 2016-08-17 | 2016-08-24 | Combining MO16-0056, MO16-0057, MO16-0061, and MO16-0062 ~AS
Consumable | TL-CS0040 | Extreme-Temperature Pipe Sealant & Threadlocker, 4 oz bottle, blue |  | 7604A55 | Mcmaster | 7604A55 | 0.5 | g | 256 | N/A |  |  | purchased on Bob's signal ~AS
Hardware | HD-BT0119 | M3 x 8 FHCS, black oxide | Fastenal | 91294A128 | Mcmaster | 91294A128 | 4 | ea | 2048 | PO15131 | 2016-08-17 | 2016-08-24 | Combining MO16-0056, MO16-0057, MO16-0061, and MO16-0062 ~AS
Hardware | HD-NT0016 | M5 Nut, Steel, Zinc Plated, thin (jam nut) | Fastenal | 90695A037 | Mcmaster | 90695A037 | 1 | ea | 512 | PO15131 | 2016-08-17 | 2016-08-24 | Combining MO16-0056, MO16-0057, MO16-0061, and MO16-0062 ~AS
Hardware | HD-TB0006 | PTFE tube, 1/4” OD x 1/8” ID, for fabrication |  | 8547K23 | Mcmaster | 8547K23 | 50 | mm | 25600 | PO15131 | 2016-08-17 | 2016-08-24 | Combining MO16-0057 and MO16-0062 ~AS
Mechanical | HD-NT0044 | Post insertion M5 T-nut for 20mm extrusion | Post assembly M5 T-nut |  | Misumi | HN-TAP5 | 1 | ea | 512 | PO15127 | 2016-08-17 | 2016-09-01 | Combining MO16-0056, MO16-0057, MO16-0061, and MO16-0062 ~AS
Electronic | EL-FA0032 | Pelonis FAN 24V 40x40mm Low flow | Pelonis | C4010L24BPLB1-7 | Pelonis | C4010L24BPLB1-7 | 2 | ea | 1024 | PO15118 | 2016-08-17 | 2016-09-21 | Combining MO16-0056, MO16-0057, MO16-0061, and MO16-0062 ~AS
Electronic | EL-FA0020 | RFB2008 Micro Blower with 30awg wire that is 250mm long |  |  | Pelonis |  | 2 | ea | 1024 | PO15118 | 2016-08-17 | 2016-09-21 | Combining MO16-0056, MO16-0057, MO16-0061, and MO16-0062 ~AS
Electronic | EL-WR0103 | 24 AWG Red wire | Allcable | HU1569247BK | Allcable | HU1569247BK | 4590 | mm | 2350080 | PO15135 | 2016-08-17 | 2016-09-02 | Combining MO16-0056, MO16-0057, MO16-0061, and MO16-0062 ~AS
Electronic | EL-WR0099 | Shielded 22AWG UL2464 4 Cond |  | [C0762A.41.10 | Allcable |  | 1000 | mm | 512000 | PO15135 | 2016-08-17 | 2016-09-02 | Combining MO16-0056, MO16-0057, MO16-0061, and MO16-0062 ~AS
Electronic | EL-WR0040 | Wire - Single Conductor 20AWG SOLID PTFE, RED | Alpha Wire | 602-2856/1-100-03 | Allcable | 602-2856/1-100-03 | 200 | mm | 102400 | PO15135 | 2016-08-17 | 2016-09-02 | Combining MO16-0056, MO16-0057, MO16-0061, and MO16-0062 ~AS
Electronic | EL-WR0123 | 16AWG Stranded – White | C2065A.12.02 | HU15691626WE | Digikey / Allcable | C2065W-1000-ND | 50 | mm | 25600 | PO15135 | 2016-08-17 | 2016-09-02
Electronic | EL-WR0105 | 24 AWG Black Wire | Allcable | [HU1569247BK | Allcable | HU1569247BK | 2490 | mm | 1274880 | PO15135 | 2016-08-17 | 2016-09-02 | Combining MO16-0056, MO16-0057, MO16-0061, and MO16-0062 ~AS
Electronic | EL-WR0119 | 24AWG Stranded – Green |  | HU1569247GN | Digikey / Allcable | C2015G-1000-ND | 50 | mm | 25600 | PO15135 | 2016-08-17 | 2016-09-02 | Combining MO16-0056, MO16-0057, MO16-0061, and MO16-0062 ~AS
Electronic | EL-WR0104 | 24AWG Orange wire |  | HU1569247OE | Allcable | C2015A-1000-ND | 2100 | mm | 1075200 | PO15135 | 2016-08-17 | 2016-09-02 | Combining MO16-0056, MO16-0057, MO16-0061, and MO16-0062 ~AS
Electronic | EL-MS0073 | 1/4” Black panduit wire wrap |  |  | Electronics Distributors Corp |  | 300 | mm | 153600 | PO15133 | 2016-08-17 | 2016-08-25 | Combining MO16-0056, MO16-0057, MO16-0061, and MO16-0062 ~AS
Electronic | EL-MS0247 | Heat Shrink Tubing – 0.19-0.09 – Black, 100' |  |  | Electronics Distributor Corp | 88-01870 | 200 | mm | 102400 | PO15133 | 2016-08-17 | 2016-08-25 | Combining MO16-0056, MO16-0057, MO16-0061, and MO16-0062 ~AS
Electronic | EL-MS0139 | 3/8” Corrugated Wrap-Around Sleeving |  |  | Electronics Distributors Corp |  | 975 | mm | 499200 | PO15133 | 2016-08-17 | 2016-08-25 | Combining MO16-0056, MO16-0057, MO16-0061, and MO16-0062 ~AS
Electronic | HD-TB0032 | Flexible Polyolefin Heat Shrink Tubing 1/8" ID Before, 1/16" ID After, 100', Black | EDC | 84-01250 | McMaster-Carr | 7856K33 | 50 | mm | 25600 | PO15133 | 2016-08-17 | 2016-08-25 | Combining MO16-0057 and MO16-0062 ~AS
Electronic | EL-MT0017 | Half Height NEMA 17 Stepper Motor, wires cut to 150mm |  |  | Changzhou FTX | SY42STH33-1504A | 2 | ea | 1024 | N/A |  |  | Plenty in stock (purchased entire year's supply only used on dual extruders) – using until Moon's half-stepper is approved ~AS (Approved to pull from current inventory. TS)
Electronic | EL-MS0212 | CONN PIN 24-30AWG CRIMP TIN | Molex | 16-02-0105 | TTI | MOL16-02-0108 | 8 | ea | 4096 | PO15149 | 2016-08-18 | 2016-09-02 | Combining MO16-0056, MO16-0057, MO16-0061, and MO16-0062 ~AS
Electronic | EL-MS0251 | CONN HOUSING 16POS .100 DUAL | Molex | 22552161 | TTI | 22552161 | 4 | ea | 2048 | PO15149 | 2016-08-18 | 2016-09-02 | Combining MO16-0056, MO16-0057, MO16-0061, and MO16-0062 ~AS
Electronic | EL-MS0059 | CONN TERM Female 22-24AWG | Molex | 16-02-0086 | TTI |  | 22 | ea | 11264 | PO15149 | 2016-08-18 | 2016-09-02 | Combining MO16-0056, MO16-0057, MO16-0061, and MO16-0062 ~AS
Electronic | EL-MS0205 | CONN TERM MALE 22-24AWG TIN | Molex | 16-02-0107 | TTI | WM2517TR-ND | 15 | ea | 7680 | PO15149 | 2016-08-18 | 2016-09-02 | Combining MO16-0056, MO16-0057, MO16-0061, and MO16-0062 ~AS
Electronic | EL-MS0123 | CONN PIN 0.062 24-26 AWG Tin Crimp | Molex | 1-66106-5 | TTI | A31991TR-ND | 23 | ea | 11776 | PO15149 | 2016-08-18 | 2016-09-02 | Combining MO16-0056, MO16-0057, MO16-0061, and MO16-0062 ~AS
Electronic | EL-MS0129 | CONN Cable clamp CPC size 17 black | Molex | 206070-8 | TTI | A32516-ND | 1 | ea | 512 | PO15149 | 2016-08-18 | 2016-09-02 | Combining MO16-0056, MO16-0057, MO16-0061, and MO16-0062 ~AS
Electronic | EL-MS0124 | 20-24 AWG Sockets for Receptacle | TE Connectivity AMP Connectors | 1-66331-4 | TTI / Digikey | 1-66331-4 | 2 | ea | 1024 | PO15149 | 2016-08-18 | 2016-09-02 | Combining MO16-0056, MO16-0057, MO16-0061, and MO16-0062 ~AS
Electronic | EL-MS0246 | CONN RING UNINS 15-20AWG #M3 | Molex | 2-323758-1 | Digikey | A107160CT-ND | 1 | ea | 512 | PO15149 | 2016-08-18 | 2016-09-02 | Combining MO16-0056, MO16-0057, MO16-0061, and MO16-0062 ~AS
Consumable | TL-CS0117 | Elmer's Glue Sticks, .77oz |  | 23810-1020 | Dick Blick Art Materials | 23810-1020 | 1 | ea | 512 | PO15619 | 2016-09-20
Consumable | TO-CS0107 | Loctite® 262™ Threadlocker High Strength 50ML Bottle |  | S-15893 | Uline | S-15893 | 0.25 | g | 128 | N/A |  |  | purchased on Bob's signal ~AS
Electronic | EL-MS0131 | CONN, PLUG, 14 POS | Sager | 206044-1 | Sager | 206044-1 | 1 | ea | 512 | PO15138 | 2016-08-17 | 2016-09-02 | Combining MO16-0056, MO16-0057, MO16-0061, and MO16-0062 ~AS
Electronic | PC-CN0001 | CONN Housing 2 POS .100 W/ latch | Sager | 050579402 | Sager | 050579402 | 1 | ea | 512 | PO15138 | 2016-08-17 | 2016-09-02 | Combining MO16-0056, MO16-0057, MO16-0061, and MO16-0062 ~AS
Electronic | EL-MS0061 | Conn Housing Male 4POS .100 | Sager | 70170003 | Digikey | WM2535-ND | 2 | pcs | 1024 | PO15138 | 2016-08-17 | 2016-09-02 | Combining MO16-0056, MO16-0057, MO16-0061, and MO16-0062 ~AS
Electronic | EL-WR0127 | Hook-up Wire 26AWG SOLID PTFE, WHT | Mouser | 602-2843/1-100-01 | Mouser | 602-2843/1-100-01 | 150 | mm | 76800 | PO15162 | 2016-08-19 | 2016-09-02 | Combining MO16-0057 and MO16-0062 ~AS
Shipping | SH-PG0063 | 8 x 7 x 6" Indestructo Mailers 100/800 |  |  | Uline | S-15087 | 1 | ea | 512 | N/A |  |  | Changing to Korrvu box
Shipping | SH-PG0004 | 8 x 8" 2 Mil Reclosable Polypropylene Bags |  |  | Uline | S-1699 | 1 | ea | 512 | N/A |  |  | Changing to Korrvu box
Shipping | SH-PA0019 | Bubble 1/8x48x750 perf 12" slit 2-24" rolls |  |  | Shipper Supply |  | 2 | sheet | 1024 | N/A |  |  | Changing to Korrvu box
Shipping | SH-PA0039 | Roll of 48"x1/4" Thick Foam, Split at 12" - 225 feet Per Roll |  |  | Shipper Supply |  | 0.0011111 | ea | 0.56889
Label | DC-LB0074 | Label, LulzBot TAZ FlexyDually Tool Head v2c, 0.6 Nozzle, Front |  |  | Sticker Giant |  | 1 | ea | 512
Label | DC-LB0075 | Label, LulzBot TAZ FlexyDually Tool Head v2c, 0.6 Nozzle, Back |  |  | Sticker Giant |  | 1 | ea | 512
Label | DC-LB0104 | Tool Head Wiring Connector Alignment Label |  |  | Sticker Giant |  | 2 | ea | 1024
Documentation | DC-MS0047 | v2 Tool Head Instruction Card |  |  | The print shop of Loveland |  | 1 | ea | 512 | PO15268 | 2016-08-25 | 2016-09-08 | Combining MO16-0056 and MO16-0057
Sample | RM-TE0027 | LulzBot Green NinjaFlex™ TPE Filament, 3mm, 0.75kg |  |  | Fenner Drives |  | 0.02 | ea | 10.24 | PO15579 | 2016-09-15
Sample | RM-AB0082 | Black ABS 3mm Filament, 5lb Reel |  |  | Village |  | 0.0066 | ea | 3.3792 | PO15578 | 2016-09-15 |  | Combining MO16-0056 and MO16-0057
Label | DC-LB0084 | LulzBot TAZ FlexyDually v2 Serial Number Label |  |  |  |  | 1 | ea | 512
Documentation | DC-MS0054 | Firmware Update Warning Cards |  |  |  |  | 1 | ea | 512 | PO15186 |  |  | Combining MO16-0056, MO16-0057, MO16-0061, and MO16-0062 +500 per Bob ~AS
Note on D37: Rfq fastenal
Note on F37: Rfq fastenal
Note on D38: Rfq fastenal
Note on D39: Rfq fastenal
Note on G70: This is a McMaster-Carr Part Number
Note on E82: Need Mfr PN.
Note on G82: Need Mfr PN.

## OLD - Don't Use
Javelin BOM |  |  |  |  | QTY to Build | 150 |  |  | Qty to Order |  |  |  | PO | Date | ETA | Notes
Printed |  |  | Dual_Extruder_Mt-v1.3 |  | Aleph Objects |  | 1 | ea | 150 | 1 | 1
Printed |  |  | Flex_plate_v0.5, Blue |  | Aleph Objects |  | 1 | ea | 150 | 1 | 1
Printed |  | PP-GP0186 | Wade extruder body for Hex nozzle v1.0 |  | Aleph Objects |  | 2 | ea | 300 | 0.86907 | 1.7381 | extruder
Printed | PP-GP0059 | PP-GP0059 | Wade Reloaded Idler Block v1.4, Taz & Mini |  | Aleph Objects |  | 2 | ea | 300 | 0.16528 | 0.33056 | extruder
Printed |  | PP-GP0061 | herringbone_large_gear |  | Aleph Objects |  | 2 | ea | 300 | 0.5588 | 1.1176 | extruder
Printed |  | PP-GP0091 | extruder_latch |  | Aleph Objects |  | 2 | ea | 300 | 0.061074 | 0.12215
Printed |  | PP-GP0062 | herringbone_small_gear |  | Aleph Objects |  | 2 | ea | 300 | 0.075106 | 0.15021 | extruder
Printed |  | PP-GP0060 | Wade Reloaded Bearing Washer |  | Aleph Objects |  | 2 | ea | 300 | 0.0045513 | 0.0091026 | extruder
Printed |  | PP-GP0162 | Spool Arm, Blue |  | Aleph Objects |  | 1 | ea | 150 | 1.9856 | 1.9856
Printed |  | PP-GP0074 | feed_tube spinner |  | Aleph Objects |  | 1 | ea | 150 | 0.06818 | 0.06818
Printed |  |  | dual_fan_shroud |  | Aleph Objects |  | 2
Mechanical |  |  | dual_lower_plate_v0.4 |  |  |  | 1 | ea
Mechanical |  |  | dual_hex_mount_plate_v0.2 |  |  |  | 1 | ea
Hardware |  | HD-MS0031 | Thumb Screw Knob for M4 SHCS, Black |  | Timberline |  | 4 | ea | 600 | 0.0952 | 0.3808 | extruder |  |  |  |  | McMaster-Carr Supply Company | 91175A062
Hardware |  | HD-BT0052 | M4 x 55 Bolt, SHCS Black-Oxide |  | Timberline |  | 4 | ea | 600 | 0.0783 | 0.3132 | extruder |  |  |  |  | McMaster-Carr Supply Company | 91290A187
Hardware |  | HD-NT0004 | M3 Nut, Zinc Plated |  | Timberline |  | 4 | ea | 600 | 0.0092 | 0.0368 | small herringbone gear, extruder idler |  |  |  |  | McMaster-Carr Supply Company | 90591A121
Hardware |  | HD-BT0012 | M3 Set Screw (Grub Screw) |  | Timberline |  | 2 | ea | 300 | 0.0167 | 0.0334 | extruder, rods and switches |  |  |  |  | McMaster-Carr Supply Company | 91390A100
Hardware |  | HD-MS0230 | M2 x 6 Bolt, SCHS Black-Oxide |  |  |  | 4 | ea
Hardware |  | PP-MP0066 | Metric Brass Heat-Set Insert for Plastics, Tapered, M2-.4 Internal Thread, 2.9MM Length |  |  |  | 4 | ea
Hardware |  | HD-BT0039 | M3 x 12 Bolt, SHCS Black-Oxide |  | Timberline |  | 6 | ea | 900 | 0.0117 | 0.0702 | [5 empty] | McMaster-Carr Supply Company | 91290A117
|  |  | M3 x 25 Bolt, FHCS Black-Oxide |  |  |  | 2 | ea
|  |  | M3 x 20 Bolt, SHCS |  |  |  | 4 | ea
Hardware |  | HD-BT0041 | M3 x 25 Bolt, SHCS Black-Oxide |  | Timberline |  | 6 | ea | 900 | 0.025 | 0.15 | extruder; bed mount, z-hard stop |  |  |  |  | McMaster-Carr Supply Company | 91290A125
Hardware |  | HD-WA0001 | M3 Washer, Steel, Zinc Plated |  | Timberline |  | 12 | ea | 1800 | 0.0013 | 0.0156 | [5 empty] | McMaster-Carr Supply Company | 91166A210
Hardware |  | HD-BT0010 | M4 x 20 Bolt, SHCS Black-Oxide |  | Timberline |  | 4 | ea | 600 | 0.0362 | 0.1448 | Extruder/Buda |  |  |  |  | McMaster-Carr Supply Company | 91290A168
Hardware |  | HD-WA0005 | M4 Washer |  | Timberline |  | 8 | ea | 1200 | 0.0033 | 0.0264 | Extruder/Buda |  |  |  |  | McMaster-Carr Supply Company | 91166A230
Hardware |  | HD-NT0011 | M4 Nut,Zinc-Plated Steel |  | Timberline |  | 8 | ea | 1200 | 0.01 | 0.08 | extruder/buda |  |  |  |  | McMaster-Carr Supply Company | 90591A141
Hardware |  | HD-BT0108 | Hobbed Bolt, M8 x 50mm Hex head, 26mm offset, Stainless Steel |  | Quattro |  | 2 | ea | 300 | 4 | 8 | extruder
Hardware |  | HD-NT0002 | M8 Nyloc Nut, Zinc Plated |  | Timberline |  | 2 | ea | 300 | 0.0547 | 0.1094 | bearings, extruder |  |  |  |  | McMaster-Carr Supply Company | 90576A117
Hardware |  | HD-WA0008 | M8 shim washer - .5mm |  | Timberline |  | 2 | ea | 300 | 0.0117 | 0.0234 | extruder, spooler,bearings |  |  |  |  | McMaster-Carr Supply Company | 91166A270
Hardware |  | HD-WA0009 | M8 shim washer – 1.0mm |  | Timberline |  | 2 | ea | 300 | 0.0117 | 0.0234 | extruder, spooler,bearings |  |  |  |  | McMaster-Carr Supply Company | 91166A270
Hardware |  | HD-WA0006 | M8 Washer, Steel, Zinc Plated |  | Timberline |  | 8 | ea | 1200 | 0.0117 | 0.0936 | extruder, spooler,bearings |  |  |  |  | McMaster-Carr Supply Company | 91166A270
Mechanical |  | HD-MS0204 | 100 Sealed Skateboard/inline/Rollerblade Skate Bearing Ball |  | vxb.com | kit708 | 6 | ea | 900 | 0.5388 | 3.2328 | 4 bearings used in robot, 3 in extruder |  |  |  |  | Received |  | Checking with Mary on inventory levels / Per Mary, we should be good on these – don't order more.
Hardware |  | HD-BT0049 | M5 x 14 Bolt, SHCS Black_Oxide |  | Timberline |  | 2 | ea | 300 | 0.025 | 0.05 | [5 empty] | Mcmaster-Carr Supply Company | 91290A230
Hardware |  | HD-MS0055 | Thumb Screw Knob for M5 SHCS, Black |  | Timberline |  | 1 | ea | 150 | 0.1072 | 0.1072 | Y-axis |  |  |  |  | McMaster-Carr Supply Company | 91175A063
Hardware |  | HD-MS0027 | Spring, Extruder, 6mm OD, 0.8mm WD, 9.7mm FL |  | Associated Spring | C0240-032-0380-M | 4 | ea | 600 | 0.35 | 1.4 | Extruder, Z-endstop
Mechanical |  | HD-RD0004 | 8mm Smooth Rod x 18-19mm |  | MBK |  | 2 | ea | 300 | 4.63 | 9.26 | extruder
Mechanical |  |  | Assy, Lulzbot Hexagon V1.0 with 0.35 nozzle | Aleph Objects | Aleph Objects |  | 2 | ea | 300 | 52 | 104
Hardware |  | HD-TB0007 | Feed Tube, PTFE |  | Professional Plastics | 0.187 ID X .250 OD NAT PTFE TUBE | 850 | mm | 127500 | 0.0035761 | 3.0397 | Filament Guide | PO06980 | 2015-03-31 | 2015-04-06 | 418 Feet | McMaster-Carr Supply Company | 5239K12
Hardware |  | HD-WA0007 | M5 Washer, Steel, Zinc Plated |  | Timberline |  | 1 | ea | 150 | 0.003 | 0.003 | frame |  |  |  |  | McMaster-Carr Supply Company | 91166A240
Hardware |  | HD-MS0058 | Wire Tie, 8” |  | Electronics Distributors Corporation |  | 6 | ea | 900 | 0.0232 | 0.1392 |  | PO06876 | 2015-03-20 | See Notes | 50K 4/3/15 - 40K 4/17/15 - 40K 5/1/15 - 40K 5/15/15 - 40K 5/29/15 | McMaster-Carr Supply Company | 7130K59
Hardware |  | HD-MS0062 | Metric Aluminum Unthreaded Spacer, 8MM OD, 8MM Length, M5 Screw Size |  | Timberline |  | 1 | ea | 150 | 1.15 | 1.15 | [5 empty] | McMaster-Carr Supply Company | 94669A757 | Still need to order (7/31
Hardware |  | HD-NT0044 | Post insertion M5 T-nut for 20mm extrusion | Post assembly M5 T-nut | Misumi | HN-TAP5 | 1 | ea | 150 | 0.046 | 0.046 | for additional spool arm |  |  |  |  | Received |  | Checking with Mary on inventory levels / Per Mary, we should be good on these – don't order more.
Hardware |  |  | Panduit wire wrap – 1/4” Black |  |  |  | 260 | mm
|  |  | 40mm Fan |  |  |  | 2 | ea
Electronic |  | EL-FA0020 | RFB2008 Micro Blower, 30 AWG wire 250mm long |  | Pelonis |  | 2 | ea
Electronic |  | EL-MT0017 | Half Height NEMA 17 Stepper Motor, wires cut to 60mm |  | Changzhou | SY42STH33-1504A | 2 | ea | 300 | 5.35 | 10.7
Electronic |  | TL-CS0083 | EMI/RFI-Shield Heat-Shrink Tubing 3/16" ID Before, 3/32" ID After, 48" L, Black, cut to 50mm |  | Mcmaster-Carr Supply Company | 7937K31 | 90 | mm | 13500 | 0.013845 | 1.2461 | [5 empty] | 44.2913 | Feet
Electronic |  | TL-CS0129 | Interference-Shielding Heat-Shrink Tubing, 3/8" ID Before, 3/16" ID After, 48" Long, Black |  | Mcmaster-Carr Supply Company | 7937K33 | 60 | mm
Electronic |  | EL-MS0061 | Conn Housing Male 4POS .100 |  | Digikey | WM2535-ND | 2 | pcs | 300 | 0.4 | 0.8
Electronic |  | EL-MS0205 | CONN TERM MALE 22-24AWG TIN |  | Digikey | WM2517TR-ND | 8 | pcs | 1200 | 0.065 | 0.52
[10 empty] | Dual Extruder BOM cost | 152.7165
Might Change
Will Change
New